EventHub - Phase Plan

Step-by-step phases: Creating, Backend, Frontend, Connecting, Security, Booking, Signature Features, Testing, Launch

Practice project  |  React + Spring Boot + MySQL

Companion to the EventHub Master Plan

Owner: Madhavan  |  26 September 2026

# Phase Overview

The project is built in 10 phases. Each phase has one clear type of work, a list of steps, an output you can see, and a "done when" check. Do not start the next phase until the check passes.

Phase 0      Phase 1      Phase 2      Phase 3      Phase 4

FOUNDATIONS  CREATING     BACKEND      FRONTEND     CONNECTING

learn the -> set up the -> database  -> all pages -> React talks

basics       project      + APIs       + design     to Spring

│

Phase 9      Phase 8      Phase 7      Phase 6      Phase 5

LAUNCH    <- TESTING   <- SIGNATURE <- BOOKING &  <- SECURITY

deploy +     tests +      waitlist,    PAYMENTS     login, JWT,

portfolio    polish       QR, certs    seat hold    roles

| Phase | Name | Main work | Time |
| --- | --- | --- | --- |
| 0 | Foundations | Java, JS and SQL basics + EventHub console app | 2-3 weeks |
| 1 | Creating the project | Tools, folders, Spring Boot + React skeleton, Docker, Git, CI | 1 week |
| 2 | Backend | Database tables + REST APIs for clubs, events, approval | 2 weeks |
| 3 | Frontend | All pages and components with Tailwind, using sample data | 2 weeks |
| 4 | Connecting | React uses the real APIs; search, filters, pagination | 1 week |
| 5 | Security | Register, login, JWT cookie, roles, protected pages | 1.5 weeks |
| 6 | Booking & Payments | Seat hold, no-oversell engine, My Tickets, Stripe | 2 weeks |
| 7 | Signature features | Waitlist, QR check-in, certificates, feedback, analytics | 2.5 weeks |
| 8 | Testing & polish | Automated tests, security checks, mobile and UI polish | 1 week |
| 9 | Launch | Deploy, README, demo video, LinkedIn | 1 week |

Total: about 15-17 weeks at 1.5-2 hours per day (including Phase 0).

# Phase 0 - Foundations

Time: 2-3 weeks

Goal: Learn the basics and build the EventHub rules as a simple Java console program.

Real-life example: Like learning to ride a bicycle in an empty ground before going on the road. The console app has the same rules as the real app, without the difficult parts.

## Steps

- Study the Learning Notes: Java basics, OOP, collections, exceptions

- Create classes: Event, Student, Booking, and enum BookingStatus

- Add menu options: 1. List events  2. Book  3. Cancel  4. Show waitlist

- Throw a custom SoldOutException when seats are full

- Use a Queue for the waitlist - cancelling gives the seat to the next student

- JavaScript practice: a small HTML page that lists events from a JSON array with a search box

- SQL practice: SELECT, WHERE, JOIN, GROUP BY on sample tables

- Learn Git and push the console app to GitHub

## Output of this phase

- EventHub console app (Java)

- Mini event list web page (HTML + JS)

- Your first GitHub repository

## Done when

- Booking, sold out, cancel and waitlist all work in the console

- You can explain class vs object and List vs Queue

Skills you practise: OOP, collections, exceptions, enums, JavaScript arrays, SQL, Git

# Phase 1 - Creating the Project

Time: 1 week

Goal: Create the real project structure so that the backend, frontend and database all run on your laptop.

Real-life example: Before building a house you prepare the land, bring the tools and draw the plan. This phase is exactly that.

## Steps

- Install JDK 21, IntelliJ IDEA, VS Code, Node.js (LTS), Docker Desktop, Postman, Git

- Create the GitHub repository "eventhub" with backend/ and frontend/ folders

- Generate the Spring Boot project from start.spring.io (Web, Data JPA, Validation, Security, MySQL, Flyway, Actuator, Mail, Cache, Lombok)

- Create the React app with Vite; install Tailwind CSS, React Router, Redux Toolkit, Axios

- Write docker-compose.yml with MySQL 8 and Mailpit (fake email inbox)

- Connect Spring Boot to MySQL in application.yml; create dev and prod profiles

- Add a /api/health endpoint and Swagger UI

- Add GitHub Actions: build and test automatically on every push

- Draw the page sketches and database diagram on paper (keep a photo in the repo)

## Output of this phase

- Running Spring Boot app at localhost:8080

- Running React app at localhost:5173

- MySQL and Mailpit running in Docker

- Green CI tick on GitHub

## Done when

- The React page shows "Backend: UP"

- docker compose up starts the database with one command

Skills you practise: Project setup, Maven, npm, Docker, configuration, CI/CD

# Phase 2 - Backend

Time: 2 weeks

Goal: Build the database and the first REST APIs: clubs, events, tags and the approval workflow.

Real-life example: The kitchen is built before the dining hall is opened. Once the kitchen works, any menu (frontend) can use it.

## Steps

- Write Flyway migration V1: users, roles, profiles, clubs, club_members, events, tags, event_tags

- Write Flyway migration V2: sample data - 5 clubs, 20 events, tags

- Create entities with relationships (One-to-One, One-to-Many, Many-to-Many)

- Create repositories with Spring Data JPA

- Create DTOs (request / response) - never return entities directly

- Create services with business rules

- Event APIs: list with search, filter by tag / club / date, sort and pagination; get by id; create; update

- Approval workflow: DRAFT -> PENDING_APPROVAL -> PUBLISHED / back to DRAFT with a reason

- Validation (@Valid) and a global exception handler that returns clean JSON errors

- Test every API in Postman and check Swagger

## Output of this phase

- Database with 8+ tables and sample data

- Working REST APIs documented in Swagger

- Postman collection saved in the repo

## Done when

- GET /api/events?tag=tech&page=0 returns the right events

- Submitting and approving an event changes its status correctly

- Wrong input returns a 400 error with a clear message

Skills you practise: Spring Boot, REST, JPA relationships, DTO pattern, validation, exception handling, Flyway

# Phase 3 - Frontend

Time: 2 weeks

Goal: Build every page and component with a good design, using sample (fake) data first.

Real-life example: An architect first makes a model of the building. You can walk through every room and fix the design before the real building is connected to water and electricity.

## Steps

- Plan the design: colours, fonts, logo, dark mode (Tailwind theme)

- Build shared components: Navbar, Footer, Button, Card, Modal, Badge, Loader, EmptyState

- Set up React Router with all routes and a 404 page

- Public pages: Home (upcoming + trending), Events with filter sidebar and pagination, Event Details, Club page

- Auth pages: Login and Register with form validation

- Student pages: Checkout with seat-hold countdown, My Tickets, Ticket with QR, Waitlist, Certificates

- Organizer pages: My Club, Create / Edit Event form, Volunteers, Dashboard layout

- Volunteer page: Gate Scanner screen (green / red result design)

- Admin pages: Approval queue, Admin overview

- Set up the Redux store with slices: auth, cart, notifications

- Make every page mobile friendly

## Output of this phase

- Complete clickable website with sample data

- Reusable component library

- Redux store ready for real data

## Done when

- You can click through every page on laptop and phone

- Dark mode works on every page

Skills you practise: React components, props, state, hooks, React Router, Redux Toolkit, Tailwind, responsive design

# Phase 4 - Connecting Frontend & Backend

Time: 1 week

Goal: Replace the sample data with real data from the Spring Boot APIs.

Real-life example: Now the model house gets real water and electricity - every tap and switch starts working.

## Steps

- Create one Axios client with the base URL and error handling

- Enable CORS in Spring Boot for the React address

- Load events, event details and clubs from the API

- Connect search, filters, sorting and pagination to the API

- Show loading skeletons, empty states and friendly error messages

- Organizer create / edit event form saves to the backend

- Admin approval queue approves and rejects for real

## Output of this phase

- The website works with the real database

## Done when

- An event added through the organizer form appears on the Events page after approval

- No sample data is left in the code

Skills you practise: Axios, async/await, useEffect, CORS, error handling

# Phase 5 - Security

Time: 1.5 weeks

Goal: Real login and correct permissions for Student, Volunteer, Organizer and Admin.

Real-life example: The college gate: everyone shows an ID card, and each ID card opens only certain rooms.

## Steps

- Register API with BCrypt password hashing

- Login API that sends a JWT inside an httpOnly cookie; logout clears it

- JWT filter in Spring Security that reads the cookie on every request

- CSRF protection with a CSRF cookie that Axios sends back

- Roles: STUDENT and ADMIN; club roles: ORGANIZER and VOLUNTEER (per club)

- Protect every API by role - for example only organizers of that club can edit its events

- React: auth slice in Redux, protected routes, hide buttons the user cannot use

- Audit log: record who approved, rejected or edited events

- Rate-limit the login API to stop password guessing

## Output of this phase

- Working register / login / logout

- Role-based access on backend and frontend

## Done when

- A student gets 403 on admin APIs; an admin gets 200

- An organizer of Coding Club cannot edit Dance Club events

Skills you practise: Spring Security, JWT, cookies, CSRF, authentication vs authorization

# Phase 6 - Booking & Payments

Time: 2 weeks

Goal: Students can book and pay safely - with no overselling, ever.

Real-life example: IRCTC tatkal booking - thousands of people click at the same moment, but a seat must never be given to two people.

## Steps

- Flyway V3: bookings and payments tables

- Book API creates a HELD booking with a 10-minute timer and reduces seats

- Optimistic locking with @Version on Event; retry when two requests clash

- Scheduled job every minute: expire old holds and give the seats back

- Free events confirm immediately

- Stripe Checkout session for paid events (test mode)

- Stripe webhook with signature check confirms the booking (Stripe CLI for local testing)

- Idempotency - the same webhook twice never confirms twice

- Cancel booking API; seats come back

- Concurrency test: 100 parallel requests on 10 seats = exactly 10 bookings

- React: Book button, countdown timer, Stripe redirect, success / cancel pages, My Tickets with status

## Output of this phase

- Working booking engine with seat hold

- Stripe test payments

- Passing concurrency test

## Done when

- Test card 4242 4242 4242 4242 confirms a booking

- An unpaid hold expires and the seat returns

- The concurrency test passes every time

Skills you practise: @Transactional, optimistic locking, @Scheduled, webhooks, idempotency, multithreading

# Phase 7 - Signature Features

Time: 2.5 weeks

Goal: Add the features that make EventHub unique.

Real-life example: This is what turns a normal project into a project that interviewers remember.

## Steps

- Smart waitlist: join / leave, show position ("You are #3")

  - When a seat frees up, offer it to #1 for 30 minutes; if not accepted, move to the next

- Notifications: emails with Spring Mail (see them in Mailpit) + in-app bell with unread count

  - Reminder email the day before the event (scheduled cron job)

- QR e-tickets: generate a QR image (ZXing) holding a random ticket code

- Gate scanner: volunteer scans with the phone camera (html5-qrcode); API answers VALID / ALREADY USED / INVALID

  - Live check-in counter for organizers

- Certificates: after the event, checked-in students download a PDF (OpenPDF) with a unique number

  - Public verify page /verify/{number}

- Feedback: 1-5 stars and a comment after the event

- Analytics dashboard: bookings per day, revenue, check-in rate, rating (Recharts); cache results with @Cacheable

## Output of this phase

- Waitlist, QR check-in, certificates, feedback and dashboards working

## Done when

- Cancelling a booking sends an offer email to the first waitlisted student

- Scanning the same ticket twice shows ALREADY USED

- Only checked-in students get a certificate

Skills you practise: Queues, scheduling, email, QR and PDF generation, JPQL aggregates, caching, charts

# Phase 8 - Testing & Polish

Time: 1 week

Goal: Make sure everything works, is secure and looks professional.

Real-life example: Before a car leaves the factory it goes through quality checks - brakes, lights, paint.

## Steps

- Unit tests for services with JUnit 5 and Mockito

- Integration tests with Testcontainers (real MySQL in tests)

- React Testing Library tests for key components (countdown, scanner result, forms)

- Security checks: Actuator and Swagger only for ADMIN; no secrets in code

- Accessibility and mobile check on every page

- Fix bugs from a full manual run of the demo script

- Clean up code, remove unused files, consistent naming

## Output of this phase

- Automated test suite running in CI

- Bug-free demo journey

## Done when

- CI is green with all tests

- Service test coverage is about 70% or more

Skills you practise: Testing pyramid, debugging, code quality

# Phase 9 - Launch

Time: 1 week

Goal: Put EventHub online and present it to the world.

Real-life example: The grand opening of the restaurant - invite people, take photos, tell everyone.

## Steps

- Deploy the backend (Render or Railway) with a managed MySQL database

- Deploy the frontend (Vercel or Netlify)

- Set environment variables for secrets (JWT key, Stripe test keys, mail)

- Write the README: problem, features, screenshots, tech stack, architecture diagram, how to run, live link

- Record a 3-5 minute demo video following the demo script

- Post on LinkedIn; add the project to your resume

- Tag version v1.0 on GitHub

## Output of this phase

- Live website link

- Professional README and demo video

- Resume and LinkedIn entries

## Done when

- A friend can open the link on their phone, register, book, get a QR ticket and download a certificate

Skills you practise: Deployment, environment configuration, documentation, presenting your work

# Phase Tracker

Fill in the dates and status as you go.

| Phase | Name | Time | Start | Finish | Status |
| --- | --- | --- | --- | --- | --- |
| 0 | Foundations | 2-3 wk |  |  |  |
| 1 | Creating the project | 1 wk |  |  |  |
| 2 | Backend | 2 wk |  |  |  |
| 3 | Frontend | 2 wk |  |  |  |
| 4 | Connecting | 1 wk |  |  |  |
| 5 | Security | 1.5 wk |  |  |  |
| 6 | Booking & Payments | 2 wk |  |  |  |
| 7 | Signature features | 2.5 wk |  |  |  |
| 8 | Testing & polish | 1 wk |  |  |  |
| 9 | Launch | 1 wk |  |  |  |